|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **THEME OR ACTION** | **LEAD** | **PARTNERS** | **TIMEFRAME** | **UPDATE** |
| Refresh Kent and Medway Housing Strategy (KMHS) | JE/RS | ALL KHG and KDG, KPOG, KF&RS | April 2020 | Consultation to KHG, EXB & Sub Group Chairs 27th Feb – 6th March    Attending CEX and Leaders in March 2020 |
| **HEALTH & WELLBEING** |  |  |  |  |
| Support Action Plan and Objectives identified by the Housing Health and Social Care Sub Group | HB/ST | ALL KHG | On going | Meetings planned for 2020, action plan to remain under review and events/training to be linked to main KHG Events/training programme for 2020/21 |
| Review the opportunities for Better Care Funding initiatives and opportunities for joint working or commissioning, for example Hospital Discharge Schemes, Procurement of Standard Equipment | KPSHG Chair/RS | KPSHG, Commissioning, NHS, Public Health, Social Care | On going | Need to take decision on work around DFG and funding opportunities for 2020 to be discussed at KPSHG and JMG meetings in March |
| Mental Health Scoping Paper | TBC | ALL KHG | TBC | Scoping paper to be shared by SW with HB as Chair of HHSC Sub Group for consideration about taking forward |
| **WORKING TOGETHER FOR SAFER HOMES** | |  |  |  |
| **INFRASTRUCTURE FIRST** |  |  |  |  |
| Kent and Medway Growth, Infrastructure and Housing Deal proposal | JE/RS | Tracy Kerly, David Godfrey & KCC, SELEP, MHCLG, Homes England | On going | GD meetings planned to May 2020 |
| **ACCELERATING HOUSING DELIVERY** | |  |  |  |
| Kent and Medway Growth, Infrastructure and Housing Deal proposal | JE/RS | Tracy Kerly, David Godfrey & KCC, SELEP, MHCLG, Homes England | On going | GD meetings planned to May 2020 |
| **AFFORDABILITY** |  |  |  |  |
| Intentionally Homelessness Protocol | KHOG | KCC/EARLY HELP/Front Door/Local Authorities | TBC | KHOG to agree representatives to work on review and update |
| Pre Eviction Protocol | KTMSG/KHOG | LA’s/HA’s | Dec 2019 | Requires sign off by KHG EXB |
| Care Leavers Protocol | KHOG | LA’s/HA’s/KCC | April 2020 | YP Draft out for consultation with KHOG, T&FG’s have met, ambition to have ready to share by April 2020 |
| Joint Protocol for 16/17 Year Olds |
| **INCOME** |  |  |  |  |
| To continue to review membership opportunities, ensure that existing members are receiving value for money | SW/RS | KHG Treasurer/KHG EXB | On going | Constant review of membership opportunities to ensure income maximised. |
| Where appropriate charge for events or training, to cover costing of external provision. | KN/RS | KHG Events Group / KHG EXB & Full membership | On going | Ensure costing to cover provision of events/training is appropriate, including income for annual awards |
| **EVENTS, COMMUNICATIONS AND SUB GROUPS** | |  |  |  |
| Develop and deliver annual Events and Workshops programme | KN | KHG Events and all KHG members | On going | To remain as standing item on KHG and EXB agendas |
| Continually review and agree KHG representation on countywide groups and the mechanism for reporting back to the wider membership | RS | KHG EXB | On going | Need to continue to review the attendance and membership opportunities for the group |
| Consultation responses – Agree mechanism for responding | RS | KHG EXB/Full Membership | On going | To agree when responses to consultations to be made |
| Undertake review of KHG sub-groups | JE/RS | KHG EXB/Full Membership | On going | Sub Group Chairs invited to KHG EXB upon request of KHG Chair |
| Develop communications action plan based on KMHS priorities, develop KHG brand awareness and link to Events sub-group | KHG EXB/KN/RS | ALL KHG | On going | WKHA to assist with communications plan and marketing of KHG |
| Develop opportunities around the use of the website | RS | KHG EXB / Events | On going | RS to pick up once KMHS endorsed and has capacity |